## Burn down chart
Release Burndown
Sprints completed | Expected Story Points Remaining | Actual Story Points Remaining
0 | 81 | 81
1 |  | 56
2
3
4 | 0
Sprint 1 Burndown
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20 | 27 | 27
19 |  | 27
18 |  | 26
17 |  | 26
16 |  | 26
15 |  | 24
14 |  | 24
13 |  | 24
12 |  | 22
11 |  | 20
10 |  | 17
9 |  | 17
8 |  | 16
7 |  | 14
6 |  | 12
5 |  | 8
4 |  | 8
3 |  | 7
2 |  | 5
1 |  | 5
0 | 0 | 5
ALSO DO A SPRINT 2 BURNDOWN AS WELL